## Defect report quiz
Defect ID | Module | Defect Description | Expected Result | Defect Status(Tester) | Screenshot link | Defect status(Developer) | Developer Comment | Tester Comment | Date of issue Raised | Date of issue Solved
1 | Home page_Register | Without (checking) selecting checkbox of "I agree" user can register and data is saved in admin panel | Error validation message should be displayed & user shouldn't be register without checking checkbox | Open | https://drive.google.com/file/d/1MkO55CwA0aQWsObc7H3LxwvcQEG7JGuG/view?usp=sharing | solved |  | Close | 2020-12-11
[5 empty] | https://drive.google.com/file/d/1KHmlqScSZBmXtu_W2pE19q0kY3MbFhKu/view?usp=sharing | solved |  |  | 2020-12-11
2 | Home page_Register | After clicking on cancel button user navigates to admin panel | Data should get clear after clicking on cancel button | Open | https://drive.google.com/file/d/120aVQrFTOj9gS2nUD1I2wAQj5vzcOm93/view?usp=sharing | solved |  |  | 2020-12-11
3 | Home page_Register | User can enter digits in name field and data is saved in admin panel | Error validation message should be dispalyed. | Open | https://drive.google.com/file/d/17SpbpkgaS4d7tghYuaCR_29_l1idUxy0/view?usp=sharing | solved |  | Close | 2020-12-11
4 | Home_participate_edit | When user clicks on edit option then earlier selected country,state, city,district is not displaying | When user clicks on edit option then earlier selected country,state, city,district should be display. | Open | https://drive.google.com/file/d/1SQWlBkOpkHuaZO9C05IvNvRXj4OA4Bfc/view?usp=sharing | solved |  |  | 2020-12-11
5 | Home_participate | City word is not displaying properly | City word should be display properly. | Open | https://drive.google.com/file/d/11J54W8IPDoW148O8d4YPSHOVio306BKh/view?usp=sharing | solved |  |  | 2020-12-11
6 | Dashboard_Add user | User can enter digits in name field | Error Validation msg should be dispalyed | Open | https://drive.google.com/file/d/1CGB5MgFQt913OVz3AcmKs7FOs8kciOg9/view?usp=sharing | solved |  |  | 2020-12-11
7 | Dashboard_Add user | User can enter digits in city field | Error Validation msg should be dispalyed | Open | https://drive.google.com/file/d/10MdXZwiDjF-WOUJZsKdkDEU4SKq_AmD2/view?usp=sharing | solved |  |  | 2020-12-11
8 | Dashboard_Delete | Proper validation msg is not dispalying |  | Open | https://drive.google.com/file/d/18z5Yr1NfQJ5cp1D3OEvgJYR5fheW_1vG/view?usp=sharing | done |  |  | 2020-12-11
9 | Dashboard_ Add user | User can enter more than 10 digits in mobile no. field | Error Validation msg should be dispalyed | Open | https://drive.google.com/file/d/13JyxlTdgMQP9zpl1ekvqDfuxHcXAdnIp/view?usp=sharing | done |  |  | 2020-12-11
10 | Dashboard_ Add user | User can enter negative numbers in mobile no. field | Error Validation msg should be dispalyed | Open | https://drive.google.com/file/d/1KOPBqYAqyYUF2JLDqQOmlsQHqbSIAE23/view?usp=sharing | solved |  |  | 2020-12-11
11 | Dashboard_Banner_Delete | Proper validation msg is not dispalying |  | Open | https://drive.google.com/file/d/1XRzgbZOQHmH4tpvYJZJtPwGOTfM46ABr/view?usp=sharing | done |  |  | 2020-12-11
12 | Dashboard_Competition_Delete record | Proper validation msg is not dispalying | Prpoper validation msg should be dispaly after deleting record | Open | https://drive.google.com/file/d/1vESCCbGjOkUWxBZEhqy7e15tRhR2rGUs/view?usp=sharing | done |  |  | 2020-12-11
13 | Dashboard_Competation_Edit | Proper validation msg is not dispalying | Proper validation msg should be dispaly after updating record | Open | https://drive.google.com/file/d/1t8tNtBWwrCk9RJfwe75kiC1bBcN3obxn/view?usp=sharing | done |  |  | 2020-12-11
14 | Dashboard_Competition | If user upload ".jfjf" type image then it's name is not displaying in table & if this type of image is not allowed here then error validation msg should be displayed. | Error validation message should be dispalyed. | Open | https://drive.google.com/file/d/13hmE7cHdhA6LXQuJeGkYm1hGnOHt-hJs/view?usp=sharing |  |  |  | 2020-12-11
15 | Dashboard_Competition_Edit_Upload image | If user update image using edit option,then this updated image name is not listed in table | Updated image name should be displayed in list | Open | https://drive.google.com/file/d/1jWG-ytIPCqmBElunMjIkHM3yHOT3Sjkb/view?usp=sharing | this is functionality is used to save and update |  |  | 2020-12-11
[5 empty] | https://drive.google.com/file/d/1lgGEASN-MXt4xTgMQ3axZjJBcpgu1KSS/view?usp=sharing | solved |  |  | 2020-12-11
16 | Dashboard_Add user | With same mobile no registration can be done and listed. | With same mobile no registration should not be done and listed. | Open | https://drive.google.com/file/d/1WYymqmwHP3KCSveHuCbNJc5KTU0Mjn0p/view?usp=sharing | solved |  |  | 2020-12-11

## Defect report Quiz (2-1-2021)
Defect ID | Module | Defect Description | Expected Result | Defect Status(Tester) | Screenshot link | Defect status(Developer) | Developer Comment | Tester Comment | Date of issue Raised | Date of issue Solved
1 | Login Form | If user doesn't enter any data in "Mobile no" field & clicks on LOgin button then nothing is happned | Error validation message should be display like "Please enter valid mobile no" | Open |  | done |  |  | 2021-01-02
2 | Sign UP Form | If user doesn't enter name & fills other data like pin no & mobile no. then this occurs(please refer screenshot) | Error validation message should be display | Open | https://drive.google.com/file/d/1FRL0yTsY7NwfPv2WHiYif14AGQK5BNJU/view?usp=sharing | done |  |  | 2021-01-02
3 | My Profile | If user doesn't particpate and clicks on My Profile option from header then this form opened with unnecessary text on left hand side |  | Open | https://drive.google.com/file/d/1Od_3tigTcOnkMGySkRfKgbsX7uNuEtwT/view?usp=sharing | done |  |  | 2021-01-02
4 | My Profile | After Editing other data in profle & clicks on Edit option then Error validation msg is dispalying of Pincode field | Edited data should be updated | Open | https://drive.google.com/file/d/1aXMhYIWeXZDx_JYmTML_MOR8OR_URiKi/view?usp=sharing |  |  |  | 2021-01-02
5 | My Profile | Alert success msg is not displaying properly | Alert success msg shoukd be display properly | Open | https://drive.google.com/file/d/1_0ZUmfRTP2IQq9vKUU25zniU1wpfo7_g/view?usp=sharing | done |  |  | 2021-01-02
6 | Add Participate | If user doesn't enter any data from form & clicks on Paticipate button each time 2 error validation msgs are displaying | Only one error validation message should be display | Open | https://drive.google.com/file/d/187DDMRJmp-SSck89u9pmg4U7d9DolmAi/view?usp=sharing | done |  |  | 2021-01-02
|  |  |  | Open | https://drive.google.com/file/d/1v53MwgavoT7fj6GxtOfhEaRoy0oAzmt5/view?usp=sharing |  |  |  | 2021-01-02
7 | sign up form(website side) | UI issue |  | Open | https://drive.google.com/file/d/1-MLkx20vkVGXF3CT0XpKoY1pCkG8OLvL/view?usp=sharing | done |  |  | 2021-01-02
8 | Login form | UI issue |  | Open | https://drive.google.com/file/d/1lFw78YiAvDjcHx18G_3Oy4bVEoKYcfad/view?usp=sharing | done |  |  | 2021-01-02
9 | Login with facebook | Login with facebook functionality is not working | Login with facebook functionality should be working | Open | https://drive.google.com/file/d/1cKJxzCDcsKQNUYY-EPG595EAsQ0O13wa/view?usp=sharing | done |  |  | 2021-01-02
10 | My Profile form | UI ISSUE |  | Open | https://drive.google.com/file/d/1MRU6Svli40IOhLVxjUZLnG_oMTilEL-R/view?usp=sharing | done |  |  | 2021-01-02
11 | Sign Up | Alert Success msg is not displaying properly | Alert Success msg should be display properly | Open | https://drive.google.com/file/d/1C47lSh_tv_2oiike495oBVS2HtTilFHS/view?usp=sharing | done |  |  | 2021-01-02
12 | Admin Panel_Banner_Edit | If user edit "Enter Banner Title" then previously uploaded image gets invisible | If user edit "Enter Banner Title" then previously uploaded image should not get invisible | Open |  | done
13 | Admin panel_Competation | If user edit age then error validation msg is displaying for pincode & select competation"please flil out this field" | Edit functionality should be working properly | Open
14 | Admin panel_Competation | User can add age in negative numbers | User should be able to add only positive numbers in age field | Open |  | done
15 | Admin panel_Competatio_Edit | Edit functionality is not working properly | Edit functionality should be working properly | Open(8-2-2021) |  | done
16 | Admin panel_Assign Competation_Edit | Not working |  | Open |  | in process
17 | Admin panel_Prize_Edit | Not working properly(user has to edit all fields then only its updated otherwise its not working properly if user want to update only one field) | Edit functionality should be working properly | Open(8-2-2021) |  | done

## 3-2-2021
Defect ID | Module | Defect Description | Defect Status(Tester) | Screenshot link | Defect status(Developer) | Developer Comment | Tester Comment | Date of issue Raised | Date of issue Solved
1 | Register form/Sign in form | If user enter only one letter/digits in password field then register form gets submitted | Close |  | done |  |  | 2021-02-03 | 2021-02-08
2 | Sign in form | If user enter incorrect mobile no & correct password then error validation msg is displaying for both fields | Close |  | done |  |  | 2021-02-03 | 2021-02-08
3 | Sign in form | If user enter correct mobile no & incorrect password then error validation msg is displaying for both fields | Open |  | done |  | Now user can login with invalid password | 2021-02-03
4 | Sign in form | If user sign in sucessfully then validation message displayed like "Successfull" | Close |  | done |  |  | 2021-02-03 | 2021-02-08
5 | Add participate form | User can enter minus number in age field | Open |  | done |  |  | 2021-02-03
6 | Add participate form | Although "pin code" field is marked with asteric mark ,record can be saved without filling this field | Close |  | done |  |  | 2021-02-03 | 2021-02-08
7 | Add participate form | User can participate in same competition for number of times | Open | https://drive.google.com/file/d/1W3dQBwIpTRbnNkckR8bolPK8b7Qg405u/view?usp=sharing |  |  | Not able to do retesting because of new issue raised now refer issue no 33 | 2021-02-03
8 | My profle | validation msg is not displaying for mandatory fields | Open |  | done |  | can not retest because now user is not able to participate | 2021-02-03
9 | My profle | space issue between "Choose file" & image of it | Open |  | done |  | can not retest because now user is not able to participate | 2021-02-03
10 | My profle | image name is overlaps on another fields | Open |  | done |  | can not retest because now user is not able to participate | 2021-02-03
11 | My profle | After editing profile user is not naviagates to home page or any other page | Open |  | done |  | can not retest because now user is not able to participate | 2021-02-03
12 | Admin panel-competation form | User can enter negative numbers in age filed | Close |  | done |  |  | 2021-02-03 | 2021-02-08
13 | Admin panel-competation form | Lables are not given for Terms & conditions ,Instructions | Close |  | done |  |  | 2021-02-03 | 2021-02-08
14 | Admin panel-competation form | If user check the checkboxes for email & whatsapp & does not fill the fields & clicks on submit buton then form gets submitted. | Open |  |  |  | Error validation msg is not displaying | 2021-02-03
15 | Admin panel-competation form | Validation message is not displaying for mandatory fields | Open |  | done |  |  | 2021-02-03
16 | Admin panel-All forms | Form labels are not mentioned | Open |  | done |  |  | 2021-02-03
17 | Admin panel-All forms | All mandatory fields are not marked with * marks as well as according to that error validation message is not displaying | Open |  | done |  |  | 2021-02-03
18 | Admin panel-User | User can enter numbers in Name field | Close |  | done |  |  | 2021-02-04 | 2021-02-08
19 | Admin panel-User | User can enter only one digit password also | Open |  | done |  | Incorrect validation msg is displaying "Remove this msg-please fill out this field" | 2021-02-04
20 | Admin panel-Banner | if user update only title and clicks on update button then previous image gets invisible | Close |  | done |  |  | 2021-02-04 | 2021-02-08
21 | Admin panel-competation form | In alert success msg "Competition Type Updated successfully".Use pascal case in msg | Close |  | done |  |  | 2021-02-04 | 2021-02-08
22 | Admin panel-competation form | In whatsapp field user can enter alphabates | Open |  |  |  |  | 2021-02-04
23 | Admin panel-competation form | Quiz name is not mentioned in table.user can not find this competation using quiz name | Close |  | done |  |  | 2021-02-04 | 2021-02-08
24 | Admin panel-competation form | user can not update any single field without selecting any value from drop down list of "competation type", "user type","level" and "choose file" | Open |  |  |  |  | 2021-02-04
25 | Admin panel-Participate | "Are you sure want to save Record" this msg is displaying after clicking on "Participate button" Do correct sentence with question mark | Close |  | done |  | Now alert msg is removed but validation msg is displaying | 2021-02-04 | 2021-02-08
26 | Admin panel-Participate | user can not update any single field without selecting any value from drop down lists present in form | Open |  |  |  |  | 2021-02-04
27 | Admin panel-Participate | My competition-no. of times same competition can be added | Open |  |  |  |  | 2021-02-04
28 | Admin panel-Prize | In "Enter Prize" field user can enter negative numbers | Close |  | done |  |  | 2021-02-04 | 2021-02-08
29 | Admin panel-Prize | User can not update any single field without selecting any value from drop down lists present in form | Open |  |  |  |  | 2021-02-04
30 | Admin panel-Dynamic competition | User can ask questions to any competitons Ex.Dancing | Open |  |  |  |  | 2021-02-04
31 | Admin panel-Area Information | According to states cities should be display in drop down list | Open |  |  | do not use this form in admin panel skip this form |  | 2021-02-04
32 | Login/Sign up form | If user does not fill any filed like mobile no then Proper error validation message should be display like "Please enter valid mobile no" | Open |  |  |  |  | 2021-02-08
33 | Add participate form | After user clicks on participate button then alert msg is displaying & clicking on this ok button of alert msg nothing is happned | Open |  |  |  |  | 2021-02-08
34 | Participate form | Age-Incorrect validation msg is displaying | Open | https://drive.google.com/file/d/1fSE-5gPyj5VXtq_mV_OgJxxmfmPCICFH/view?usp=sharing |  |  |  | 2021-02-08
35 | Admin panel | Competition form-Spelling mistake-Terms & conditions | Open | https://drive.google.com/file/d/1F0XjSpIHZeKRmNDqk4ShOTSBiogC4TN5/view?usp=sharing |  |  |  | 2021-02-08
36 | Admin panel | Competition form-Spelling mistake-Instrucions should be there | Open | https://drive.google.com/file/d/1F0XjSpIHZeKRmNDqk4ShOTSBiogC4TN5/view?usp=sharing |  |  |  | 2021-02-08
37 | Participate form | Address is not mandatory then also validation msg is displaying | Open |  |  |  |  | 2021-02-08
38 | Register form | Confirm password functionality is reamaining | Open

## Instructions
Forms | Fields | Instructions
Login | Mobile no | Entered mobile no. will be used as user name
Password
Register | Pin code | Pin code will be autofilled in profile
| Name | Name will be autofilled in profile
| Mobile no | Entered mobile no. will be used as user name
Participate
Admin Panel
User
Banner | Banner Title | Banner Title,Banner Sub Title,Banner Image will be displayed on frontend(Home page-Slider)
Banner Sub Title
Banner Image
Competition Type | Competition Type | Competition Type added by user will be displayed on "Competition" form
Competition | Competition Title | Data entered in these filelds will be displayed on FrontEnd(Card)
Competition Sub Title
Competition Image
| Tab Input Text | Data entered in this field will be dislayed on Tabs on homepage(FrontEnd)
Rest of the fields will be used on single page of competition

## 2-3-2021
| Defect ID | Module | Defect Description | Expected Result | Defect Status(Tester) | Screenshot link | Defect status(Developer) | Developer Comment | Tester Comment | Date of issue Raised | Date of issue Solved
| 1 | Profile-Birth date | User can enter birth date of future dates also |  | close |  |  |  |  | 2021-02-15
| 2 | Profile-Email | User can enter invalid email also & it gets submitted |  | close |  |  |  |  | 2021-02-15
| 3 | Registration form | If User enter invalid format of password then user does not get validation message about format of password |  | close |  |  |  |  | 2021-02-15
| 4 | Login | If user alreday registered & logged in then where should user navigates?? |  | close |  |  |  |  | 2021-02-15
| 5 | Profile | After state distrtict should come |  | close |  | done | city-input field,state after district |  | 2021-02-15
| 6 | Profile | All cities & districts are not displaying in drop down list |  | close |  | done | all disricts show in dropdown only |  | 2021-02-15
| 7 | Home | After user register when user click on "My competition" then "Current competition" title is displaying instead of that message should be display like "You have not participated in any competation " / "You have to fill up all details in profile" |  | close |  |  |  |  | 2021-02-15
| 8 | Profile | If user entered same contact number in "Alternate contact number" then error validation message is not displaying |  | close |  | done | onchange input error msg is display downside of input |  | 2021-02-15
2021-02-19 | 9 | Frontend_Quiz | User can start quiz & after starting quiz without submitting quiz user is able to navigate on home page by clicking on home option avaialable in header |  | close |  | done |  |  | 2021-02-19
| 10 | Frontend_Quiz | Number of questions on a single page are different for every quiz. Load more/ Next option should be available |  | Temp close(1-4-2021) |  |  | duplicate defect |  | 2021-02-19
| 11 | Frontend_Quiz | If user does not select any option from drop down list & clicks on submit button then error validation message is not displaying |  | open(10-3-2021) |  |  | * |  | 2021-02-19
| 12 | Edit Profile & competition | User can edit "standard" number of times in profile so that he can be able to participate in any competition. User should be able to edit standard only one time. |  | open(10-3-2021) | https://drive.google.com/file/d/10Z5qIoP33Fp_AP9Yoyp5DNzitW5hczw6/view?usp=sharing |  | * |  | 2021-02-19
| 13 | competition | If user is female & selected "standard"- (female 18+) then also user is not able to participate in Female 18+ competition |  | close(6-3-2021) | https://drive.google.com/file/d/1JV-b1L-xdD38iXtL2iV0IoBp9UjnLalD/view?usp=sharing | done |  |  | 2021-02-19
| 14 | competition | According to age of user ,age is not displaying in detials of competition page |  | close(10-3-2021) | https://drive.google.com/file/d/16C7Hvtua6WV-Xb2IpG7cLOs1w6fdG8M5/view?usp=sharing | done |  |  | 2021-02-19
https://drive.google.com/file/d/1AhFETp4CKLnBBJqjEOuf_hh9iJYsvwV1/view?usp=sharing
| 15 | Edit profile | While registering user has entered same (highlighted)number & this number can also submitted in alternate mobile no. Steps-1.Enter same numer in "alternate number" 2.Click on "EDIT" button |  | Close(8-3-2021) | https://drive.google.com/file/d/16tV0UKbtAzcv-zjlI6aPumR1e8UJlv_C/view?usp=sharing | done |  |  | 2021-02-19
| 16 | competition | User should be able to see uploaded file.This option is not available now. |  | Close(8-3-2021) | https://drive.google.com/file/d/1yIcFqBSA9IJW0h2Lq3o4TAmXEzggdHez/view?usp=sharing | done |  | After uploading of file, immediately file should be displayed.Now user can see uploaded file after submitting competition. | 2021-02-19
| 17 |  | Message should be User has Participated Successfully |  | close | https://drive.google.com/file/d/1HyrEBsxYscdYdLxwtgHuZpmlHuX4Tl6t/view?usp=sharing | done |  |  | 2021-02-19
| 18 |  | Msg should be User is already participated in this competition |  | close | https://drive.google.com/file/d/1QDauE6kKFxzrtZZY-08pnG_0RIH4gX_a/view?usp=sharing | done |  |  | 2021-02-19
| 19 |  | Profile-Message should be Enter valid email address |  | close(6-3-2021) | https://drive.google.com/file/d/1mpJqQS3IvoAoPVCX0IDHP4nblZpnYJPW/view?usp=sharing | close |  |  | 2021-02-19
| 20 |  | Details of competition-content should be in one line |  | close | https://drive.google.com/file/d/1_k1lQvCddxXT_-dDOVu_8CKorRtlSizA/view?usp=sharing | done |  |  | 2021-02-19
| 21 |  | symbol is not looking good at middle position |  | close | https://drive.google.com/file/d/1aWnzA4wSmQTMOPRqbK-MEP44EExccXnI/view?usp=sharing | done |  |  | 2021-02-19
| 22 | My competitions | "Current competition" title is not displaying (only past competition title is displaying) |  | close |  |  |  |  | 2021-02-19
| 23 | Winner information_points form | Points should be greater than conversion points.Validation & functionality also not done. |  | Open(1-4-2021) | https://drive.google.com/file/d/18YFsXCpIHNf6pOJbdgBKvysXoB5KAvlL/view?usp=sharing
| 24 | 24.competition information- | File type is not mentioned | fle type for ex. JPEG,JPG,Mp3 are allowed | close | https://drive.google.com/file/d/10RFiJ0c8RhKJuZJSNq_6QHQVrxUiS-qE/view?usp=sharing | done(10-3-21) | note is entered also onchange image the alert msg is displyed | If user chose file like Zip then zip file is not uploaded but after clicking on update button form gets submitted & in front end this added competition is displaying but without banner image | 2021-02-19
| 25 | Admin-competition | Error validation msg is not displaying for email ,whatsapp & upload file option. |  | close | https://drive.google.com/file/d/1xHvNoQkYDRX7Y3pcuP1jUEb6hLKXHhBB/view?usp=sharing | done(10-3-21) | note is entered | Now if user enter only email id & whatsapp no. but does not check checkbox then form gets submitted & validation is remaining for email Id &Whatsapp no(Invalid email id & whatsapp no. can ges submitted) | 2021-02-19
| 26 | 26.Dynamic Quiz Competition | User can add blank answer & updated it successfully |  | open(10-3-2021) | https://drive.google.com/file/d/1biHYNdd6AyCog9iAA-zZ0K1GphQP18sk/view?usp=sharing | done | first is radiobutton and then textbox input feilds respectively so first validation msg display of radiobutton and then text box | Now validation is done but in improper way. user first has to select radiobutton & then fill up answer. In that way there is probability of incorrect answer submitted as correct answer.
| 27 | Admin_Competition Information | Although user can not flll data in mandatory fields afer clicking on "Add" button then error validation message is not displaying |  | Close(10-3-2021) |  | done |  |  | 2021-02-19
| 28 | Sign up | If user entered existed mobile no. & clicks on sign up then all data gets cleared like name,surnname,password |  | open(10-3-2021) |  | done |  | Now if already existed email id is entered & clicks on sign up button then mobile no. field gets cleared | 2021-02-22
| 29 | Profile | User is able to edit age & standard number of times in profile |  | open(10-3-2021) |  | done(15-3-21) | * |  | 2021-03-02
| 30 | Admin_Competition information | If user does not enter data in mandatory fields then error validation message is not displaying |  | Close(10-3-2021) |  | done |  |  | 2021-03-02
| 31 | Admin_Competition information | User can check the check boxes of whatsapp & email without enetring whatsapp no. & email id & error validaton message is not displaying |  | Duplicate |  | done |  |  | 2021-03-02
| 32 | Admin_Competition information | There is no linking between Class & Tab input text. User can enetr different information in these two fields | User should select same option from both drop down lists. | open(10-3-2021) |  | done | note is entered | Only note is written but after clicking on "add" button form gets submitted & due to incorrect information gets submitted at backend, issues are created at frontend | 2021-03-02
| 33 | Admin_Dynamic quiz competition | User is able to submit form without selecting correct answer.Error validation message is not displaying. |  | open(10-3-2021) |  | done |  | Now error validation message is displaying for radiobuttons only but not for Checkboxes | 2021-03-02
| 34 | Competitions(singing,dancing,nail art etc) | After choosing files user naviagtes to "My COMPETITION " PAGE | User should be able to see uploaded images,videos so that user should be at same page | close(6-3-2021) |  | done |  |  | 2021-03-02
| 35 | Admin_Quiz display | User is not able to see correct or incorrect answers |  | close(6-3-2021) |  | done |  |  | 2021-03-02
| 36 | Admin_Dynamic quiz competition | Without selectig correct answers question is submitted.Validation is not done. |  | Duplicate |  | done |  |  | 2021-03-02
| 37 | Admin_Assign winner & competition | List is not displaying |  | close(6-3-2021) |  | done | assign winner |  | 2021-03-03
| 38 | Admin_Dynamic quiz competition | If user clicks on cancel button then user navigates to "Add competition" form |  | close(6-3-2021) |  | done | reset form |  | 2021-03-03
| 39 | Admin_Dynamic quiz competition | User can add same question number of times |  | open(10-3-2021) |  | done(10-3-21) | Now only error validation message is displaying & user navigates to another page (answer quiz) page & question is saved successfully message is displaying. Question added successfully. |  | 2021-03-03
| 40 | Admin_Dynamic quiz competition -Edit | Spelling mistkae in "Quetion saved successfully" it should be "Question" |  | close(8-3-2021) |  | done |  |  | 2021-03-03
| 41 | Admin_Dynamic quiz competition_Edit quiz | When user clikcs on cancel button then user navigates to dashboard |  | close(8-3-2021) |  | done |  |  | 2021-03-03
| 42 | Competition_Quiz | Error validation message is not displaying for drop down list if user does not select any one option from drop down list |  | open |  |  | * |  | 2021-03-03
| 43 | Competition_Quiz | competition subject is not displaying ata frontend but in backend subject is displaying |  | close Temp(8-3-2021) | https://drive.google.com/file/d/1iczUTvvUJOlqJVtT4LkTI9fKPM2OvH4S/view?usp=sharing |  | invalid |  | 2021-03-03
https://drive.google.com/file/d/1yZxJf1w_R1oBxoXt5o6DEzTM-ynu1NtF/view?usp=sharing
| 44 | Competition_Quiz | After starting quiz user can clicks on links in footer & get out of quiz |  | close(8-3-2021) |  | done |  |  | 2021-03-03
| 45 | Competition_Quiz | After 10 questions"Next" / "Load more" option is not available |  | open(10-3-2021) |  |  | * |  | 2021-03-03
| 46 | Competition_Quiz | If user does not select any checkbox from answers then Error validation message is not displaying |  | Duplicate |  |  | checkbox required add then all checkbox are checked that issue is created |  | 2021-03-03
| 47 | Admin panel_all forms | On clicking on cancel button user navigates to some another form |  | open |  | done |  |  | 2021-03-03
| 48 | Admin panel_Assign winner | User is able to submit form without selecting winner |  | open(10-3-2021) | https://drive.google.com/file/d/1e5katmcgm8pQ0a7hWBMlVVbiJGqRk4l1/view?usp=sharing | done | Erro validation message is not displaying for "select competition" drop down list |  | 2021-03-03
| 49 | Admin panel_Ponits | User is able to add points for same competition number of times |  | Close(10-3-23021) |  | done | onchange error msg display | After submiiting all points & clicking on submit button error validaion message is displaying | 2021-03-03
| 50 | Competition | If user select any competition other than quiz & upload image & shared with whatsapp then whtaspp tab is not opening in new tab |  | Close(10-3-23021) |  | done |  |  | 2021-03-03
| 51 | Competition | Validation or note is rquired according to different competition types.For Ex. if user has participated in carrom competition then "Only videos are allowed", if user participated in "Drawing" competition then "Only Images are allowed" |  | open(10-3-2021) |  | done(10-3-21) | Error validation message should be in red colcour |  | 2021-03-03
| 52 | Competition | After uploading video,audio,images validation message is not displaying |  | open(10-3-2021) |  |  | note is added for upload .files |  | 2021-03-03
| 53 | Admin_Level form | User can add same level type number of times |  | open(10-3-2021) |  | done(10-3-21) | Only validation msg is dislaying but same levels get added in list. |  | 2021-03-04
| 54 | Profile | -validation is not done for female & male 18+. See the Birthdate & standard. |  | open | https://drive.google.com/file/d/13RpNlT-QydqK70Xdn-QL2EE8jU8-YCnL/view?usp=sharing | done(15-3-21) | * |  | 2021-03-04
| 55 | Profile | Profile-If user select gender male & standard female18+ then also profile gets updated. Error validation message is not displaying. |  | open | https://drive.google.com/file/d/1BzldMejpNmVS8AaTTOjYXaj1hADd64AQ/view?usp=sharing | done(15-3-21) | * |  | 2021-03-04
| 56 | Videography competition | Although user is selected gender male & standard male 18+ then also user is not able to participate is videography competition |  | open(10-3-2021) |  | done | database feild is set |  | 2021-03-04
| 57 | Admin_participate | If user select gender male & standard female18+ then also form gets submiited |  | close(form changed) |  |  | * |  | 2021-03-04
| 58 | Admin_Assign competition | If no other competitior is available in competitions & user clicks on add competitior then in competition title no. is displaying. |  | Close(10-3-2021) |  | done |  |  | 2021-03-04
| 59 | Admin-Competition type | User can add same Competition type number of times |  | Close(10-3-2021) |  | done(10-3-21) |  |  | 2021-03-04
| 60 | Admin-Competition type & competition | When user delete competition or quiz from Admin panel then already participated users should able to see their score but not a questions & answers |  | close(active decative added) |  | active /inactive button added | * |  | 2021-03-04
| 61 | Admin_Assign Winner | If user does not select radiobutton of (participant) winner name & clicks on add button then database occur is occured |  | Close(10-3-2021) |  | done |  |  | 2021-03-04
| 62 | Mail notification | Email should be send if (1)user want to change password, (2)if user is winner & (3)if user is partcipated in any quiz/ competition |  | Close(2-4-2021) |  |  | * |  | 2021-03-08
| 63 | Quiz display | Spelling mistake of "answer" |  | Close(2-4-2021) |  | done(10-3-21)
| 64 | Admin_Assign competition | Pin code field does not contain any information if user does not enter pin code as well as validation of pin code is required if pin code is mandetory field |  | Close(2-4-2021) |  | done(10-3-21)
| 65 | Admin_Dynamic quiz competition | Cancel button is not working for dynamic quiz competitions |  | Close(2-4-2021)
| 66 | Quiz | By clicking on back arrow on header user can go back and leave quiz |  | temp close
| 67 | Admin_Navigation drawer | Menus in drawers are not displaying properly. Some menu text gets cut |  | Close(2-4-2021)

## 22-3-2021
Defect ID | Module | Defect Description | Expected Result | Defect Status(Tester) | Screenshot link | Defect status(Developer) | Developer Comment | Tester Comment | Date of issue Raised | Date of issue Solved
1 | Competition type_Add competition type | After entering new competition type name user is getting error validation message like "Competition Type Already Exists." |  | Temp close |  | done | onchange function is used | Now if already entered competition name is enterd and after that erasing that name & reenter new competition name then also error validation message is displaying like"Competition already exists" | 2021-03-22
2 | Competition type_Add competition type,Class Group Information | Cancle button navigation issue remaining |  | Close(1-4-2021) |  | done |  |  | 2021-03-22
3 | Competition type_Add competition type | Special symbols can be added in title |  | Close(1-4-2021) |  | done |  |  | 2021-03-22
4 | Class Group Information | After entering all mandetory data and clicking om "add" button database error is occured |  | Close(1-4-2021) | https://drive.google.com/file/d/1boz5yrbxvQGRvpW6dRH4vGnyaxrLQr19/view?usp=sharing | done |  |  | 2021-03-22
5 | Competition | Icon is not displaying for "View question" |  | Close(1-4-2021) |  | done |  |  | 2021-03-22
6 | Competition | when user select "all" then "tab input text " is showing another options |  | Close(1-4-2021) |  | done |  |  | 2021-03-22
7 | Competition | Although mandetory fields are not filled by user then also form gets submitted(image,terms & conditions,instructions) |  | Close(2-4-2021) |  | done(2-4-21) |  |  | 2021-03-22
8 | Competition | Newly added competition details are not displaying by clicking on view option |  | Close(1-4-2021) |  | done |  |  | 2021-03-22
9 | Dynamic quiz competition | User can submit question without giving options for answers. Steps:-1. Add question step 2:- Click on back arrow from "Quiz answers" page/ click any other opton from navigation drawer |  | Open |  |  | if clicking on browser back button then User can submit question without giving options for answers. |  | 2021-03-22
11 | User information | Password field does not allow "^" this special symbol |  | Open(2-4-2021) |  | done(2-4-21) |  |  | 2021-03-22
12 | Dynamic quiz | If User has selected text box for answer but here it is showing radiobutton for answers.so user can not update it without giving answer in text box. |  | Close(1-4-2021) | https://drive.google.com/file/d/1D0OjOmYHFCiF-2zSLI4AAsvxLOgW3oel/view?usp=sharing | done |  |  | 2021-03-22
13 | Assign winner | If not a single competitor is available for a particular competition then validation message is not displaying |  | Open(1-4-2021) | done | note is added "Please select the competition title first then click on view participate." |  |  | 2021-03-23
14 | Front end_My competition | In competition details date is displaying in format YYYT-MM-DD |  | Close(1-4-2021) | https://drive.google.com/file/d/17bLP0lQwWGKEmCtm2TFxvNVaqs24pQev/view?usp=sharing | done |  |  | 2021-03-23
15 | Front end_My competition | In competition details "competition level" is displaying blank.Remove it because this field is not displaying in backend. |  | Close(1-4-2021) | https://drive.google.com/file/d/1qgaoFvutaAk0hc0sjOfzfoS5tI45oaca/view?usp=sharing | done |  |  | 2021-03-23
16 | Check quiz_User Upload Files Information | If user does not uploaded any file/video/audio then message is not displaying |  | Close(1-4-2021) |  | done |  |  | 2021-03-23
17 | Assign winner | Once a competition end date is ends then only end date expires competition should be display in drop down list |  | Close(1-4-2021) |  | done(2-4-21) | displayed only enddate ends and active competitions |  | 2021-03-23
18 | Dashboard-completed competiton | completed competiton should contain only past competition whose end dates are ends |  | Close(1-4-2021) |  | done |  |  | 2021-03-23
19 | Dashboard-Ongoing competitions | Ongoing competitions should contain only current competition whose end daes are not ends |  | Close(1-4-2021) |  | done |  |  | 2021-03-23
20 | Backend-Dynamic quiz | Validaion is necesary if user has choosen image file in question then answer type should be radiobutton. |  | temp Close(1-4-2021) |  | done | note is added | only note is added but if user by mistake choose other options oher than radiobutton then issue will be there | 2021-03-23
21 | Backend-user information | Add bulk- By adding excel,image,video and clicking on add button error is occured | If other than excel file any type of file is added then error validation message should be dislayed | Close(2-4-2021) | https://drive.google.com/file/d/15Xn3niu5JGIgIZV_obuDlR-nvro56SM2/view?usp=sharing | done(2-4-21) | file extension validation completed | Now error valiadtion message is displaying but at improper place https://drive.google.com/file/d/1Pw1BVU1Ai-nr7iIHGja0z7cMBS-SccVP/view?usp=sharing | 2021-03-30
22 | Backend-Banner | Delete option is disable .User is not able to delete banner. |  | Close(1-4-2021) |  | done |  |  | 2021-03-30
23 | Backend-Points | Improper error validation message is displaying(user is not able to understand for which field error message is displaying) |  | Open(1-4-2021) | https://drive.google.com/file/d/1kESoO_Ihflw71ROnCEqGsQqIg9XVhPJy/view?usp=sharing | ** |  |  | 2021-03-30
24 | Frontend-Edit profile | By filling all mandatory fields & clicking on edit button improper validation message is displaying |  | Close(1-4-2021) | https://drive.google.com/file/d/1pp7pRDCNE_WOmRt6XojXnZIf-M21jN2j/view?usp=sharing | done |  |  | 2021-03-30
25 | Frontend-Edit profile | In drop down list of status invalid state names are displaying |  | temp Close(1-4-2021) | https://drive.google.com/file/d/1FWRsv3OiLuVRIhp7oux05Jpl_IzucXzN/view?usp=sharing | done |  |  | 2021-03-30
26 | FrontEnd-Forgot password | If user enter invalid email then error validation message is not displaying in Red colour |  | Close(1-4-2021) | https://drive.google.com/file/d/1oi7hnKJWREn0rMCqcpolMag5eJB_FWU5/view?usp=sharing | done(1-4-21) |  |  | 2021-03-30
27 | FrontEnd-Forgot password | If user enter valid email id then success validation message is not displaying in green coclour |  | Close(1-4-2021) | https://drive.google.com/file/d/1G6mNmCDDhgdZ1BrqzIxd14zgBU0lJGDa/view?usp=sharing | done(1-4-21) |  |  | 2021-03-30
28 | Forgot password | User is not getting mail of forgot password |  | Close(2-4-2021) |  | issue is cleared | cpanel issue |  | 2021-03-30
29 | Assign winner | User is not getting mail of winner |  | Close(2-4-2021) |  | issue is cleared | cpanel issue |  | 2021-03-30
30 | Competition subject | In competition subject all data is not displaying |  | Close(2-4-2021) |  | done | maxlength added |  | 2021-04-01
31 | Backend_ALL FORMS | Date format is YYYY-DD-MM | It should be DD-MM-YYY | Open(2-4-2021) | https://drive.google.com/file/d/1n9NcSuTcphcZMSPEBZsXrvf-BfTnrPXj/view?usp=sharing | done(2-4-21) |  | Do for when user is entering data in end date field also | 2021-04-01
32 | Front end-profile | Date format is MM-DD-YYYY | It should be DD-MM-YYY | Open(2-4-2021) |  |  | machine date is take input field date |  | 2021-04-01
33 | FrontEnd-Quiz participate | while playing quiz if student open new tab & search questions & answers as well as if student click on back arrow while playing quiz then user navigates to previous page |  | Temp close(1-4-2021) |  |  |  |  | 2021-04-01
34 | Single page of registration & sign up | Error validation message should be display in red colour |  | Close(2-4-2021) |  | done(2-4-21) |  |  | 2021-04-01
35 | Backend form-Banner Image | In form banner image field is mandatoy but user can submit form without choosing file for banner |  | Close(2-4-2021) |  | done(2-4-21) |  |  | 2021-04-01
36 | Backend form-Class group | Same class group can be added |  | Close(2-4-2021) | https://drive.google.com/file/d/11AY2QR_ohPb4HRAw6285hlqooz7-u03H/view?usp=sharing | done(2-4-21)* |  |  | 2021-04-01
37 | Backend form-competition subject | Subject 's content is not displaying full |  | Close(2-4-2021) | https://drive.google.com/file/d/1aTfo_1HJppTj1AZnQdD0UKyn1NvBk7_i/view?usp=sharing | done(2-4-21) |  |  | 2021-04-01
38 | Backend form-Class group | User can not add new class group |  | Open |  |  | In Front profile form for standard is static dropdown list is used |  | 2021-04-01
39 | Backend form-COMPETITION FORM | validation is not done(refer screenshot) |  | Open | https://drive.google.com/file/d/144ZGnzsZhOo2EObtCZMzakicubUDQCrV/view?usp=sharing |  |  |  | 2021-04-01
40 | Forgot password functionality | If user enter old password in "new password" & "reenter new password " fields then also success message is displaying | User should get error valid message like "You have entered an old password.Please enter new password" | Close(2-4-2021) |  | done(2-4-21) |  |  | 2021-04-01
41 | Forgot password functionality | User can use link from mail many times for resetting password. So user can edit password number of times. |  | Close(2-4-2021) |  | done(2-4-21) |  |  | 2021-04-01
42 | Backend-Dynamic quiz form | If user 1. choose select file format option 2.From that select image/video option 3.and without choosing any file clicks on "Add" button form gets submitted |  | Open(2-4-2021) | https://drive.google.com/file/d/1V6PAg23XLKBnNbDcUvQ-D2OHJ9g7oGp_/view?usp=sharing |  |  |  | 2021-04-02
43 | Backend-Dynamic quiz form | if user 1. choose select file format option 2.From that select image/video option 3.choose file 4.select text area,text box, checkbox then image / video is not uploaded | If there is condition like if When the user selected any one option from 'File Format' then the user must select Radiobutton from 'Answer Type'. then this type of validation is necessary | Open(2-4-2021) |  |  |  |  | 2021-04-02
44 | User-Add bulk | while importing excel sheet using bulk option then if first column & last row is blank in excel sheet then it shows blank data in user list columns |  | Open(2-4-2021) | https://drive.google.com/file/d/1Q3BGSa1BlXY5lHER85GU8Chrha0lKA20/view?usp=sharing |  |  |  | 2021-04-02
45 | User-add user -Password field | if user enter ^ symbol then password field showing error validation message like "invalid password" |  | Duplicate | https://drive.google.com/file/d/1XaA5ZuQ83HOHIMRBQ58Iqv1a_CDWdrmV/view?usp=sharing | done(2-4-21) |  |  | 2021-04-02
46 | Frontend | If user is already partcipated in competition & clicks on highlighted lable then user navigates to details of competition page & after clicking on submit button error validation message is displaying | on clicking on lavbles user should get error validation message | Open(2-4-2021) | https://drive.google.com/file/d/1ESG9jUMQb_ijwVbS8uaWv3RnfV8oEnr5/view?usp=sharing |  |  |  | 2021-04-02
47 | Assign winner form- | Grammer mistake-it should be 2nd Runner up not 2st Runner up |  | Close(2-4-2021) | https://drive.google.com/file/d/1-EG_SjEIXfX-KA1OJnJwGVlBdulN1_Vn/view?usp=sharing | done |  |  | 2021-04-02
48 | User-Add bulk | bulk issue with invalid data present in ecxel sheet(like invalid emil,mobile no) |  | Open(2-4-2021) | https://drive.google.com/file/d/1Q3BGSa1BlXY5lHER85GU8Chrha0lKA20/view?usp=sharing |  |  |  | 2021-04-02
49 | User-Add bulk | Bulk isuue with exchaniging data in excel sheet |  | Open(2-4-2021) | https://drive.google.com/file/d/16V9p2mC6XlqI607p_QKLwujsNCfu-3eT/view?usp=sharing |  |  |  | 2021-04-02
50 | Check quiz & files form | Improper alignment of buttons. |  | Open(2-4-2021) | https://drive.google.com/file/d/14WbxQ48rjMfHE_I4zlD00dH2TaEHkPhJ/view?usp=sharing |  |  |  | 2021-04-02
51 | Frontend-Forgot passsword | if user enter ^ symbol then password field showing error validation message like "invalid password" |  | Open(2-4-2021) |  |  |  |  | 2021-04-02
52 | Frontend-Profile form | User can choose zip/rar file for profile menu & form gets submitted | Error validation message should be display | Open(2-4-2021) |  |  |  |  | 2021-04-02
53 | Frontend-Profile form | Validation message is not displaying for age greater than 14 years to 18 years(according to age .standard validaion message is not displaying) |  | Open(2-4-2021) |  |  |  |  | 2021-04-02
54 | Frontend-quiz | while playing quiz (if answer type is checkbox)if user does not select any "checkbox" then error validation message is not displaying |  | Open(2-4-2021) |  |  |  |  | 2021-04-02
55 | Fronend-competition details page | If competition is for All user then age field is displaying from 0 To 0. |  | Open(2-4-2021) |  |  |  |  | 2021-04-02
56 | Winner information_points form | Points should be greater than conversion points.Validation & functionality also not done. |  | Open(10-3-2021)
57 | Frontend_Quiz | If user does not select any option from drop down list & clicks on submit button then error validation message is not displaying |  | Open(10-3-2021)
58 | Edit Profile & competition | User can edit "standard" number of times in profile so that he can be able to participate in any competition. User should be able to edit standard only one time. |  | Open(10-3-2021)

## age -std criteria
Age | Standard
2021-06-03 | Nur -1 st
2021-10-07 | 2nd-5th
11-14 | 6th-9th